## Sheet1
WBS Code | Task Name | Start Date | End Date | Assigned To
1.0 | Project Planning & Kickoff | 2025-03-10 | 2025-03-19 | Team Lead
1.1 | Define Scope | 2025-03-10 | 2025-03-19 | Team Lead
1.2 | Identify Team Roles | 2025-03-10 | 2025-03-19 | Project Manager
1.3 | Develop Timeline | 2025-03-10 | 2025-03-19 | Project Manager
1.4 | Tool Setup (Figma, GitHub) | 2025-03-10 | 2025-03-19 | All Members
2.0 | Requirements Engineering | 2025-03-20 | 2025-03-31 | BA Lead
2.1 | Gather User Requirements | 2025-03-20 | 2025-03-31 | BA Lead
2.2 | Document Functional & Non-Functional Requirements | 2025-03-20 | 2025-03-31 | Documentation Team
3.0 | System Design & Modeling | 2025-04-01 | 2025-04-14 | System Architect
3.1 | Create UML Diagrams | 2025-04-01 | 2025-04-14 | System Architect
3.2 | Define Software Architecture | 2025-04-01 | 2025-04-14 | System Architect
4.0 | UI Prototyping | 2025-04-15 | 2025-04-30 | UI/UX Lead
4.1 | Design Wireframes in Figma | 2025-04-15 | 2025-04-30 | UI/UX Lead
4.2 | Build Interactive Prototypes | 2025-04-15 | 2025-04-30 | UI/UX Team
4.3 | Collect User Feedback | 2025-04-15 | 2025-04-30 | Research Team
5.0 | Project Management | 2025-05-01 | 2025-05-15 | Project Manager
5.1 | Create WBS | 2025-05-01 | 2025-05-15 | Project Manager
5.2 | Allocate Resources | 2025-05-01 | 2025-05-15 | Project Manager
5.3 | Identify Risks | 2025-05-01 | 2025-05-15 | QA Lead
5.4 | Monitor Progress | 2025-05-01 | 2025-05-15 | Project Manager